## Raw Data
SR No. | Job No. | Amdocs Assigned date | Amdocs Ecd | Month | Market | Job Type | Job Submited date | Amdocs Correction received date | Current status | % of job | No. of terminals | Quality Score | Glow OTP | Amdocs OTP | Footages | LU's | ASE Footages 1 | ASE Footages 2 | ASE Energization | Page Count | Project Type | Remark if any | Week | Status with Days | Year | Total FC Revenue (₹) | Total Actual Revenue (₹) | Final Status
508 | 449148 | 2025-12-23 | 2025-12-26 | Dec'25 | Florida | F1-IQGEO |  |  | Hold | [11 empty] | F1 |  | 2025-W52 | ECD Lapsed | 2025 |  | 0 | Hold
632 | 120074 | 2026-02-19 | 2026-02-25 | Feb'26 | LA | F2 Waldo Snip |  |  | Hold |  | 59 |  |  |  |  | 182 |  |  |  |  | F2 Waldo |  | 2026-W09 | ECD Lapsed | 2026 |  | 38036.4 | Hold
657 | 667032 | 2026-03-02 | 2026-03-04 | Mar'26 | FLORIDA | F2 | 2026-03-04 |  | Submitted | 100% | 40 | 67% | 100% | 100% | 7746 | [5 empty] | F2 |  | 2026-W10 | Job Submitted AMDOCS ECD | 2026 |  | 41849.61 | Invoicing Done
658 | 245208 | 2026-03-02 | 2026-03-06 | Mar'26 | GEORGIA | F2 | 2026-03-06 |  | Submitted | 100% | 19 | 50% | 100% | 100% | 7621 | [5 empty] | F2 |  | 2026-W10 | Job Submitted AMDOCS ECD | 2026 |  | 41251.485 | Invoicing Done
665 | 381941 | 2026-03-07 | 2026-03-13 | Mar'26 | Georgia | F2 | 2026-03-13 |  | Submitted | 100% | 61 |  | 100% | 100% | 12549 | [5 empty] | F2 |  | 2026-W11 | Job Submitted AMDOCS ECD | 2026 |  | 64831.965 | Invoicing Done
666 | 153845 | 2026-03-07 | 2026-03-10 | Mar'26 | ILLINOIS | F2 | 2026-03-10 |  | Submitted | 100% | 54 | 70% | 100% | 100% | 24073 | [5 empty] | F2 |  | 2026-W11 | Job Submitted AMDOCS ECD | 2026 |  | 119974.305 | Invoicing Done
706 | 251493 | 2026-03-24 | 2026-03-27 | Mar'26 | NC | F2 | 2026-03-27 |  | Submitted | 100% | 71 |  | 100% | 100% | 27824 | [5 empty] | F2 |  | 2026-W13 | Job Submitted AMDOCS ECD | 2026 |  | 137922.84 | Invoicing Done
816 | 91239 | 2026-06-19 | 2026-06-23 | Jun'26 | FL | F2 Waldo Snip | 2026-06-23 |  | Submitted | 100% | 142 | 80% |  |  |  | 465 |  |  |  |  | F2 Waldo |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 95929.5 | Invoicing Done
817 | 420826 | 2026-06-22 | 2026-06-24 | Jun'26 | Florida | F2 Waldo Snip | 2026-06-24 |  | Submitted | 100% | 70 |  |  |  |  | 248 |  |  |  |  | F2 Waldo |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 53549.4 | Invoicing Done
818 | 602249 | 2026-06-24 | 2026-06-26 | Jun'26 | Wisconsin | F2 Waldo Snip | 2026-06-26 |  | Submitted | 100% | 131 |  |  |  |  | 576 |  |  |  |  | F2 Waldo |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 117607.8 | Invoicing Done
819 | 406140 | 2026-06-23 | 2026-06-24 | Jun'26 | Florida | F1-IQGEO | 2026-06-24 |  | Submitted | 100% |  | 71% | 100% | 100% | 100 | [5 empty] | F1 |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 6045 | Invoicing Done
820 | 728795 | 2026-06-23 | 2026-06-25 | Jun'26 | Florida | F1-IQGEO | 2026-06-25 |  | Submitted | 100% |  | 36% | 100% | 100% | 1848.5 | [5 empty] | F1 |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 11573.757 | Invoicing Done
821 | 441656 | 2026-06-24 | 2026-06-25 | Jun'26 | Wisconsin | F1-IQGEO | 2026-06-25 |  | Submitted | 100% |  | 84% | 100% | 100% | 100.4 | [5 empty] | F1 |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 6046.2648 | Invoicing Done
822 | 287655 | 2026-06-26 | 2026-06-29 | Jun'26 | Florida | F1-IQGEO | 2026-06-29 |  | Submitted | 100% |  |  | 100% | 100% | 100 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
823 | 802227 | 2026-06-26 | 2026-06-29 | Jun'26 | Florida | F1-IQGEO | 2026-06-29 |  | Submitted | 100% |  | 47% | 100% | 100% | 100.4 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 6046.2648 | Invoicing Done
824 | 35218 | 2026-06-29 | 2026-06-30 | Jun'26 | North Carolina | F1-IQGEO | 2026-06-30 |  | Submitted | 100% |  | 60% | 100% | 100% | 218.4 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 6419.3808 | Invoicing Done
825 | 461083 | 2026-06-25 | 2026-06-28 | Jun'26 | ILLINOIS | F2 Waldo Snip | 2026-06-28 |  | Submitted | 100% | 191 |  |  |  |  | 584 |  |  |  |  | F2 Waldo |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 119170.2 | Invoicing Done
826 | 791263 | 2026-06-30 | 2026-07-02 | Jun'26 | Wisconsin | F2 Waldo Snip | 2026-07-02 |  | Submitted | 100% | 130 |  |  |  |  | 404 |  |  |  |  | F2 Waldo |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
827 | 315092 | 2026-06-30 | 2026-07-02 | Jun'26 | ILLINOIS | F2 Waldo Snip | 2026-07-02 |  | Submitted | 100% | 147 |  |  |  |  | 527 |  |  |  |  | F2 Waldo |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
828 | 641355 | 2026-06-30 | 2026-07-01 | Jul'26 | Wisconsin | F1-IQGEO | 2026-07-01 |  | Submitted | 100% |  | 90% | 100% | 100% | 100 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
829 | 854823 | 2026-06-30 | 2026-07-01 | Jul'26 | ILLINOIS | F1-IQGEO | 2026-07-01 |  | Submitted | 100% |  | 91% | 100% | 100% | 1162 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
830 | 73658 | 2026-06-30 | 2026-07-02 | Jul'26 | North Carolina | F1-IQGEO | 2026-07-02 |  | Submitted | 100% |  | 80% | 100% | 100% | 2359 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
831 | 708697 | 2026-07-01 | 2026-07-02 | Jul'26 | ILLINOIS | F1-IQGEO | 2026-07-02 |  | Submitted | 100% |  | 85% | 100% | 100% | 1731 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
832 | 751873 | 2026-07-01 | 2026-07-03 | Jul'26 | Florida | F1-IQGEO | 2026-07-03 |  | Submitted | 100% |  | 62% | 100% | 100% | 100 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
833 | 644725 | 2026-07-01 | 2026-07-03 | Jul'26 | Florida | F1-IQGEO | 2026-07-03 |  | Submitted | 100% |  | 61% | 100% | 100% | 785 | [5 empty] | F1 |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
834 | 330526 | 2026-07-01 | 2026-07-03 | Jul'26 | ILLINOIS | F2 Waldo Snip | 2026-07-03 |  | Submitted | 100% | 171 | 60% | 100% |  |  | 586 |  |  |  |  | F2 Waldo |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
835 | 272257 | 2026-07-01 | 2026-07-06 | Jul'26 | Florida | F2 | 2026-07-06 |  | Submitted | 100% | 70 |  | 100% |  | 15000 | [5 empty] | F2 |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
836 | 512204 | 2026-07-06 | 2026-07-08 | Jul'26 | North Carolina | F1-IQGEO | 2026-07-08 |  | Submitted | 100% |  | 80% | 100% | 100% | 1345 | [5 empty] | F1 |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
837 | 373529 | 2026-07-06 | 2026-07-08 | Jul'26 | North Carolina | F1-IQGEO | 2026-07-08 |  | Submitted | 100% |  | 80% | 100% | 100% | 100 | [5 empty] | F1 |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Ready for Billing – Sent to Client
838 | 219062 | 2026-07-06 | 2026-07-08 | Jul'26 | North Carolina | F1-IQGEO | 2026-07-08 |  | Submitted | 100% |  |  | 100% | 100% | 185 | [5 empty] | F1 |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
839 | 238358 | 2026-07-07 | 2026-07-08 | Jul'26 | ILLINOIS | F1-IQGEO | 2026-07-08 |  | Submitted | 100% |  |  | 100% | 100% | 100 | [5 empty] | F1 |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
840 | 189265 | 2026-07-07 | 2026-07-09 | Jul'26 | ILLINOIS | F2 Waldo Snip | 2026-07-09 |  | Submitted | 100% | 111 | 87% | 100% | 100% |  | 238 |  |  |  |  | F2 Waldo |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
841 | 452997 | 2026-07-08 | 2026-07-10 | Jul'26 | ILLINOIS | F2 Waldo Snip | 2026-07-10 |  | Submitted | 100% | 104 |  | 100% |  |  | 380 |  |  |  |  | F2 Waldo |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
842 | 321163 | 2026-07-09 | 2026-07-11 | Jul'26 | ILLINOIS | F2 Waldo Snip | 2026-07-11 |  | Submitted | 100% | 145 |  | 100% | 100% |  | 395 |  |  |  |  | F2 Waldo |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
843 | 516764 | 2026-07-12 | 2026-07-13 | Jul'26 | ILLINOIS | F1-IQGEO | 2026-07-13 |  | Submitted | 100% | [10 empty] | F1 |  | 2026-W29 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
844 | 884935 | 2026-07-12 | 2026-07-14 | Jul'26 | ILLINOIS | F2 Waldo Snip | 2026-07-14 |  | Submitted | 100% | 174 |  | 100% |  |  | 468 |  |  |  |  | F2 Waldo |  | 2026-W29 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
845 | 719621 | 2026-07-13 | 2026-07-15 | Jul'26 | North Carolina | F1-IQGEO | 2026-07-15 |  | Submitted | 100% | [10 empty] | F1 |  | 2026-W29 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
846 | 800169 | 2026-07-14 | 2026-07-15 | Jul'26 | Florida | F1-IQGEO | 2026-07-15 |  | Submitted | 100% | [10 empty] | F1 |  | 2026-W29 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
847 | 163769 | 2026-07-14 | 2026-07-15 | Jul'26 | Florida | F1-IQGEO | 2026-07-15 |  | Submitted | 100% | [10 empty] | F1 |  | 2026-W29 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
848 | 369126 | 2026-07-14 | 2026-07-16 | Jul'26 | Florida | F2 Waldo Snip |  |  | IP |  | 90 |  |  |  |  | 289 |  |  |  |  | F2 Waldo |  | 2026-W29 | ECD Lapsed | 2026 |  | 0 | IP
849 | 671056 | 2026-07-14 | 2026-07-16 | Jul'26 | Florida | F2 Waldo Snip |  |  | IP |  | 39 |  |  |  |  | 144 |  |  |  |  | F2 Waldo |  | 2026-W29 | ECD Lapsed | 2026 |  | 0 | IP
850 | 646442 | 2026-07-14 | 2026-07-16 | Jul'26 | Florida | F2 Waldo Snip |  |  | IP |  | 83 |  |  |  |  | 341 |  |  |  |  | F2 Waldo |  | 2026-W29 | ECD Lapsed | 2026 |  | 0 | IP
851 | 763701 | 2026-07-16 | 2026-07-17 | Jul'26 | Wisconsin | F2 Waldo Snip |  |  | IP |  | 116 |  |  |  |  | 295 |  |  |  |  | F2 Waldo |  | 2026-W29 | Due Today | 2026 |  | 0 | IP
852 | 63475 | 2026-07-16 | 2026-07-18 | Jul'26 | ILLINOIS | F2 Waldo Snip |  |  | IP |  | 159 |  |  |  |  | 449 |  |  |  |  | F2 Waldo |  | 2026-W29 | 1 days remaining | 2026 |  | 0 | IP
12 | 889356 | 2026-06-17 | 2026-06-19 | Jun'26 | Florida | Placement <1000ft | 2026-06-19 |  | Submitted | 100% |  | 56% |  |  |  |  | 0 | 415 |  |  | ASE |  | 2026-W25 | Job Submitted AMDOCS ECD | 2026 |  | 6157.065 | Invoicing Done
13 | 761434 | 2026-06-18 | 2026-06-22 | Jun'26 | Alabama | Placement <1000ft | 2026-06-22 |  | Submitted | 100% |  | 34% |  |  |  |  | 273 |  |  |  | ASE |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 5978.226 | Invoicing Done
14 | 147156 | 2026-06-24 | 2026-06-26 | Jun'26 | Florida | Placement <1000ft | 2026-06-26 |  | Submitted | 100% |  | 73% |  |  |  |  | 327 |  | 1 |  | ASE |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 6455.874 | Invoicing Done
15 | 656234 | 2026-06-24 | 2026-06-26 | Jun'26 | Florida | Placement <1000ft | 2026-06-26 |  | Submitted | 100% |  | 62% |  |  |  |  | 0 | 300 | 3 |  | ASE |  | 2026-W26 | Job Submitted AMDOCS ECD | 2026 |  | 6789 | Invoicing Done
16 | 261973 | 2026-06-24 | 2026-06-29 | Jun'26 | Florida | Placement <1000ft | 2026-06-29 |  | Submitted | 100% |  | 65% |  |  |  |  | 190 |  |  |  | ASE |  | 2026-W27 | Job Submitted AMDOCS ECD | 2026 |  | 5715.78 | Invoicing Done
17 | 711872 | 2026-07-02 | 2026-07-06 | Jul'26 | Florida | Placement <1000ft | 2026-07-06 |  | Submitted | 100% |  | 69% | 100% |  |  |  | 818 |  | 1 |  | ASE |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 8008.416 | Ready for Billing – Sent to Client
18 | 323744 | 2026-07-03 | 2026-07-06 | Jul'26 | Florida | Placement <1000ft | 2026-07-06 |  | Submitted | 100% |  | 81% | 100% |  |  |  | 350 |  | 1 |  | ASE |  | 2026-W28 | Job Submitted AMDOCS ECD | 2026 |  | 6528.6 | Ready for Billing – Sent to Client
19 | 447223 | 2026-07-10 | 2026-07-14 | Jul'26 | Florida | Placement <1000ft | 2026-07-14 |  | Submitted | 100% | [10 empty] | ASE |  | 2026-W29 | Job Submitted AMDOCS ECD | 2026 |  | 0 | Sent to Client – QC Feedback
20 | 321837 | 2026-07-14 | 2026-07-16 | Jul'26 | Florida | Placement <1000ft |  |  | IP | [11 empty] | ASE |  | 2026-W29 | ECD Lapsed | 2026 |  | 0 | IP
Formulas:
Week = TEXT([Amdocs Ecd],"yyyy") & "-W" & TEXT(WEEKNUM([Amdocs Ecd],2),"00")